## Sheet1
Activity ID | Activity Name | Duration | Start | Finish | Predecessor Details | Successor Details | Total Float
Eskay Creek PFS - Current |  | 143 | 01-May-26 A | 2026-11-26 |  |  | 0
Key Milestones |  | 143 | 01-May-26 A | 2026-11-26 |  |  | 0
SNIP-101 | Study Award | 0 | 01-May-26 A |  |  | SNIP-249: SF, SNIP-258: SF, SNIP-248: SF, SNIP-255: SF, SNIP-103: SS, SNIP-115: SS, SNIP-134: SS, SNIP-105: FS 2
SNIP-104 | Receipt of Bronson Road Design | 0 |  | 11-Jun-26 A |  | SNIP-159: FS
SNIP-102 | Receipt of Draft Mine Plan | 0 |  | 15-Jun-26 A |  | SNIP-115: FS, SNIP-118: FS
SNIP-113 | Study implementation plan | 0 |  | 03-Jul-26 A | SNIP-111: FF
SNIP-103 | Receipt of Testwork results & MRE | 0 |  | 06-Jul-26 A | SNIP-101: SS | SNIP-118: SS
SNIP-110 | Set-up (Stage Gate No.1) Internal Approval | 0 |  | 29-Jul-26 A | SNIP-111: FS, SNIP-105: FS | SNIP-182: FS
SNIP-153 | Process (Stage Gate No.2) Internal Approval | 0 |  | 20-Aug-26 A | SNIP-154: FF, SNIP-133: FS | SNIP-234: FS
SNIP-182 | Layout (Stage Gate No.3) Internal Approval | 0 |  | 2026-09-09 | SNIP-166: FS 9, SNIP-110: FS, SNIP-220: FF -4 | SNIP-234: FF | 26
SNIP-207 | Site Infrastructure Design Complete | 0 |  | 2026-09-09 | SNIP-166: FF 20 | SNIP-261: FF | 53
SNIP-117 | Receipt of Final Mine Plan/Production Schedule | 0 |  | 11-Sep-26* |  | SNIP-242: FS | 0
SNIP-221 | Final Site Layout - Issued for Use | 0 |  | 2026-09-14 | SNIP-220: FF | SNIP-234: FF | 22
SNIP-233 | Priced Mechanical Equipment List - Issued for Estimating | 0 |  | 2026-09-23 | SNIP-231: FF | SNIP-261: FF | 43
SNIP-234 | Engineering (Stage Gate No.4) Internal Approval | 0 |  | 2026-09-24 | SNIP-221: FF, SNIP-182: FF, SNIP-161: FS -10, SNIP-215: FS -10, SNIP-230: FS -10, SNIP-223: FS, SNIP-153: FS, SNIP-237: FS -10, SNIP-220: FS, SNIP-105: FS, SNIP-166: FS, SNIP-133: SS, SNIP-115: SS, SNIP-229: FS | SNIP-255: FF 10, SNIP-235: FS | 14
SNIP-219 | Project Execution Plan (PEP) - Issued for Use | 0 |  | 2026-09-28 | SNIP-218: FF | SNIP-261: FF | 40
SNIP-238 | MTOs Complete - Issued for Estimating | 0 |  | 2026-10-08 | SNIP-239: FF, SNIP-237: FF, SNIP-220: FF, SNIP-105: FF, SNIP-166: FF, SNIP-133: SF, SNIP-115: SF, SNIP-229: FF, SNIP-230: FF | SNIP-261: FF | 33
SNIP-235 | CAPEX (Stage Gate No.5) Internal Approval | 0 |  | 2026-10-14 | SNIP-224: FS, SNIP-234: FS | SNIP-241: FS | 2
SNIP-226 | OPEX (Stage Gate No.6) Internal Approval | 0 |  | 2026-10-14 | SNIP-224: FS | SNIP-241: FS | 2
SNIP-245 | Draft Report (Stage Gate No.7) Internal Approval | 0 |  | 2026-10-29 | SNIP-255: FF -10 | SNIP-256: FF | 10
SNIP-246 | CAPEX - Final | 0 |  | 2026-11-06 | SNIP-250: FF, SNIP-244: FF | SNIP-261: FF | 13
SNIP-247 | OPEX - Final | 0 |  | 2026-11-06 | SNIP-251: FF, SNIP-244: FF | SNIP-261: FF | 13
SNIP-248 | Financial Model - Draft | 0 |  | 2026-11-06 | SNIP-101: SF, SNIP-111: SF, SNIP-241: FF, SNIP-250: FF | SNIP-261: FF | 13
SNIP-249 | Financial Model - Final | 0 |  | 2026-11-06 | SNIP-101: SF, SNIP-111: SF, SNIP-241: FF, SNIP-250: FF, SNIP-244: FF | SNIP-261: FF | 13
SNIP-256 | Draft Report Issued for Client Review | 0 |  | 2026-11-12 | SNIP-245: FF, SNIP-255: FS | SNIP-258: FS | 0
SNIP-260 | Issue Final Technical Report | 0 |  | 2026-11-26 | SNIP-259: FS | SNIP-261: FF | 0
SNIP-261 | PFS Completion | 0 |  | 2026-11-26 | SNIP-207: FF, SNIP-238: FF, SNIP-219: FF, SNIP-233: FF, SNIP-249: FF, SNIP-248: FF, SNIP-247: FF, SNIP-246: FF, SNIP-260: FF |  | 0
Inputs From Others |  | 50 | 11-Jun-26 A | 2026-09-11 |  |  | 14
SNIP-136 | Bronson Connector Road Data | 0 | 11-Jun-26 A |  |  | SNIP-159: SS
SNIP-127 | Mine Operations Data (UG Input from SRK) | 0 | 30-Jun-26 A |  |  | SNIP-166: FS, SNIP-138: SS, SNIP-201: FS
SNIP-106 | Snip Design Inputs (Infrastructure from SRK) | 0 |  | 07-Jul-26 A |  | SNIP-166: FS, SNIP-126: FS, SNIP-201: FS, SNIP-188: FS
SNIP-203 | TSF Model & Cost Estimate (Others: KP) | 0 | 11-Sep-26* |  |  | SNIP-270: FS, SNIP-240: FF 20, SNIP-310: FS | 8
SNIP-204 | Eskay Creek Model & Cost Estimate (Others:SRK - Process) | 0 | 11-Sep-26* |  |  | SNIP-240: FF 20, SNIP-270: FS | 8
SNIP-320 | Eskay Creek Model & Cost Estimate (Others:SRK - Mining) | 0 | 11-Sep-26* |  |  | SNIP-240: FF 20, SNIP-270: FS | 8
SNIP-157 | Recovery Model/Method (3rd Parties) | 8 | 17-Aug-26 A | 2026-09-11 | SNIP-156: FF | SNIP-242: FS | 14
Project Management |  | 97 | 05-May-26 A | 2026-09-22 |  |  | 44
SNIP-105 | Project Kick-off Meeting | 1 | 05-May-26 A | 05-May-26 A | SNIP-101: FS 2 | SNIP-158: FS 5, SNIP-183: FS 70, SNIP-120: FS, SNIP-116: FS, SNIP-115: FS, SNIP-124: FS, SNIP-166: FS, SNIP-111: FS, SNIP-110: FS, SNIP-142: FS 25, SNIP-112: FS, SNIP-128: FS 5, SNIP-237: FS, SNIP-240: FF, SNIP-238: FF, SNIP-234: FS
SNIP-111 | Develop Study Implementation Plan (SIP) | 15 | 15-Jun-26 A | 03-Jul-26 A | SNIP-105: FS, SNIP-112: FF | SNIP-249: SF, SNIP-258: SF, SNIP-248: SF, SNIP-255: SF, SNIP-115: SS, SNIP-110: FS, SNIP-113: FF
SNIP-148 | Project Risk and Opportunity Register | 5 | 03-Aug-26 A | 2026-09-11 | SNIP-166: SF |  | 51
SNIP-223 | Final Design Review | 1 | 2026-09-15 | 2026-09-15 | SNIP-220: FS | SNIP-234: FS | 21
SNIP-158 | QP Site-Visit | 3 | 15-Sep-26* | 2026-09-17 | SNIP-105: FS 5 |  | 47
SNIP-191 | Project Risk Workshop | 1 | 2026-09-22 | 2026-09-22 | SNIP-133: FS, SNIP-166: FS 10, SNIP-214: FS |  | 44
PFS Baseline Schedule |  | 40 | 06-May-26 A | 02-Jul-26 A
SNIP-112 | Finalize PFS Schedule - Issue for Internal Review | 15 | 06-May-26 A | 27-May-26 A | SNIP-105: FS | SNIP-132: FS, SNIP-111: FF
SNIP-132 | Finalize PFS Schedule-Internal Review,Update and Issue to Client | 25 | 28-May-26 A | 02-Jul-26 A | SNIP-112: FS
PFS |  | 113 | 15-Jun-26 A | 2026-10-14 |  |  | 30
Engineering |  | 113 | 15-Jun-26 A | 2026-10-14 |  |  | 30
Process |  | 53 | 15-Jun-26 A | 2026-09-04 |  |  | 45
Metallurgical Testwork Review |  | 15 | 06-Jul-26 A | 10-Jul-26 A
SNIP-118 | Metallurigcal Testwork Advise by Client (3rd Parties) | 15 | 06-Jul-26 A | 10-Jul-26 A | SNIP-102: FS, SNIP-103: SS | SNIP-129: FF -7
Design Criteria |  | 44 | 15-Jun-26 A | 21-Aug-26 A
SNIP-115 | Process Design Criteria-Issue for Internal Review | 5 | 15-Jun-26 A | 19-Jun-26 A | SNIP-102: FS, SNIP-101: SS, SNIP-111: SS, SNIP-105: FS | SNIP-123: FS, SNIP-116: FS, SNIP-124: FS, SNIP-128: FS, SNIP-133: FS, SNIP-134: FS, SNIP-259: SS, SNIP-237: SS, SNIP-240: SF, SNIP-238: SF, SNIP-234: SS, SNIP-161: FS
SNIP-123 | Process Design Criteria-Internal Review,Update and Issue for Client Review | 10 | 22-Jun-26 A | 13-Jul-26 A | SNIP-115: FS | SNIP-133: FF, SNIP-129: FS, SNIP-128: SS
SNIP-129 | Process Design Criteria-Client Review | 5 | 13-Jul-26 A | 07-Aug-26 A | SNIP-118: FF -7, SNIP-123: FS | SNIP-134: FS
SNIP-134 | Process Design Criteria-Final Issue | 1 | 17-Aug-26 A | 21-Aug-26 A | SNIP-129: FS, SNIP-101: SS, SNIP-115: FS | SNIP-161: SS, SNIP-255: FF, SNIP-143: FS
PFD |  | 44 | 26-Jun-26 A | 21-Aug-26 A
SNIP-133 | PFD-Issue for internal Review | 10 | 26-Jun-26 A | 14-Jul-26 A | SNIP-123: FF, SNIP-115: FS | SNIP-137: FS, SNIP-155: SS 5, SNIP-191: FS, SNIP-153: FS, SNIP-154: FS, SNIP-138: FF 3, SNIP-144: FS, SNIP-259: SS, SNIP-237: SS, SNIP-240: SF, SNIP-238: SF, SNIP-234: SS
SNIP-137 | PFD-Internal Review,Update and Issue for Client Review | 5 | 15-Jul-26 A | 07-Aug-26 A | SNIP-133: FS | SNIP-145: FS, SNIP-271: FF -2
SNIP-145 | PFD-Client Review (Not Received) | 5 | 10-Aug-26 A | 14-Aug-26 A | SNIP-137: FS | SNIP-154: FS
SNIP-154 | PFD-Final Issue | 10 | 17-Aug-26 A | 21-Aug-26 A | SNIP-145: FS, SNIP-133: FS | SNIP-255: FF, SNIP-153: FF, SNIP-227: FF
Mass and Water Balance |  | 35 | 06-Jul-26 A | 21-Aug-26 A
SNIP-138 | Process Plant Mass and water Balances-Issue for Internal Review | 10 | 06-Jul-26 A | 21-Jul-26 A | SNIP-127: SS, SNIP-133: FF 3 | SNIP-147: FS, SNIP-156: FS
SNIP-147 | Process Plant Mass and Water Balances- Internal Review,Update and Issue for Client Review | 3 | 22-Jul-26 A | 07-Aug-26 A | SNIP-138: FS | SNIP-144: FS, SNIP-155: SS 5, SNIP-150: FS
SNIP-150 | Process Plant Mass and Water Balances-Client Review (Not Received) | 5 | 10-Aug-26 A | 14-Aug-26 A | SNIP-147: FS | SNIP-156: FS
SNIP-156 | Process Plant Mass and Water Balances-Final Issue | 6 | 17-Aug-26 A | 21-Aug-26 A | SNIP-150: FS, SNIP-138: FS | SNIP-157: FF, SNIP-240: FF
Equipment Sizing |  | 10 | 27-Jul-26 A | 2026-09-04 |  |  | 45
SNIP-155 | Equipment Sizing | 10 | 27-Jul-26 A | 2026-09-04 | SNIP-147: SS 5, SNIP-133: SS 5 | SNIP-255: FF, SNIP-161: SS 2 | 45
Mechanical & Piping |  | 54 | 08-Jul-26 A | 2026-09-23 |  |  | 9
Design Criteria |  | 1 | 16-Jul-26 A | 16-Jul-26 A
SNIP-128 | Mechanical & Piping Design Criteria- Adopt Eskay Creek | 1 | 16-Jul-26 A | 16-Jul-26 A | SNIP-115: FS, SNIP-105: FS 5, SNIP-123: SS | SNIP-161: SS
MEL |  | 54 | 08-Jul-26 A | 2026-09-23 |  |  | 9
SNIP-201 | Snip MEL Inputs | 5 | 08-Jul-26 A | 14-Jul-26 A | SNIP-106: FS, SNIP-127: FS | SNIP-281: FS, SNIP-190: FS
SNIP-271 | Eskay MEL Inputs (from PFDs) | 2 | 31-Jul-26 A | 04-Aug-26 A | SNIP-137: FF -2 | SNIP-281: FS, A1000: FS, SNIP-200: FS
SNIP-281 | Mechanical Equipment List-Issue for Internal Review | 5 | 04-Aug-26 A | 19-Aug-26 A | SNIP-271: FS, SNIP-201: FS | SNIP-161: FS, A1000: FS
SNIP-161 | Mechanical Equipment List-Issue for Cilent Review | 5 | 17-Aug-26 A | 21-Aug-26 A | SNIP-134: SS, SNIP-128: SS, SNIP-155: SS 2, SNIP-115: FS, SNIP-281: FS | SNIP-144: SS, SNIP-143: FS, SNIP-167: FS, SNIP-186: FS, SNIP-234: FS -10, SNIP-165: FF 5, SNIP-236: SS, SNIP-259: FS
SNIP-143 | Mechanical Equipment List Finalized for Electrical Design | 10 | 17-Aug-26 A | 28-Aug-26 A | SNIP-161: FS, SNIP-134: FS | SNIP-180: FF 1, SNIP-240: FF 10, SNIP-228: FF 5
SNIP-167 | Mechanical Equipment List-Client Review | 5 | 24-Aug-26 A | 2026-09-01 | SNIP-161: FS | SNIP-172: FS | 9
SNIP-172 | Mechanical Equipment List-Final Issue | 5 | 2026-09-02 | 2026-09-09 | SNIP-167: FS | SNIP-231: SS | 9
SNIP-231 | Priced Mechanical Equipment List | 15 | 2026-09-02 | 2026-09-23 | SNIP-172: SS | SNIP-228: FF, SNIP-240: FF 10, SNIP-233: FF | 9
MTO |  | 15 | 11-Aug-26 A | 2026-09-04 |  |  | 16
SNIP-195 | Off Plot Piping MTO | 15 | 11-Aug-26 A | 2026-09-04 | SNIP-166: FS | SNIP-240: FF 15 | 16
Equipment Sizing |  | 10 | 17-Aug-26 A | 2026-09-04 |  |  | 0
SNIP-144 | Mechanical Equipment Sizing Calculations | 10 | 17-Aug-26 A | 2026-09-04 | SNIP-173: FF, SNIP-147: FS, SNIP-161: SS, SNIP-133: FS | SNIP-200: FF | 0
Layout |  | 103 | 30-Jun-26 A | 2026-09-14 |  |  | 50
Overall Site Plan |  | 103 | 30-Jun-26 A | 2026-09-14 |  |  | 50
SNIP-176 | Reciept of Verified Refrences From Client | 5 | 03-Jul-26 A | 10-Jul-26 A |  | SNIP-300: FF 3
SNIP-300 | Preliminary Overall Site Plan -Issue for Internal | 8 | 30-Jun-26 A | 15-Jul-26 A | SNIP-176: FF 3 | SNIP-189: FS
SNIP-166 | Site Plan Confirmed to Release Other Discipline's Design-Issue for Internal Review | 25 | 07-Jul-26 A | 11-Aug-26 A | SNIP-106: FS, SNIP-127: FS, SNIP-105: FS | SNIP-202: FS, SNIP-178: FS, SNIP-179: FS, SNIP-148: SF, SNIP-159: SS, SNIP-168: FF, SNIP-217: FS, SNIP-173: FS, SNIP-215: FS, SNIP-207: FF 20, SNIP-237: FF, SNIP-191: FS 10, SNIP-182: FS 9, SNIP-220: FS, SNIP-195: FS, SNIP-237: FS, SNIP-240: FF, SNIP-238: FF, SNIP-234: FS, SNIP-239: FS
SNIP-173 | Site Plan -Internal Review,Update and Issue for Client Review | 5 | 12-Aug-26 A | 31-Aug-26 A | SNIP-166: FS | SNIP-144: FF, SNIP-189: FS, SNIP-330: FS
SNIP-189 | Site Plan -Client Review | 5 | 31-Aug-26 A | 31-Aug-26 A | SNIP-300: FS, SNIP-173: FS | SNIP-220: FS
SNIP-330 | Layout Review Workshop w Client | 1 | 31-Aug-26* | 2026-08-31 | SNIP-173: FS |  | 59
SNIP-220 | Site Plan / GA Confirmed to Finalize Other Discipline's Design-Final issue | 15 | 31-Aug-26 A | 2026-09-14 | SNIP-189: FS, SNIP-166: FS | SNIP-239: FS, SNIP-221: FF, SNIP-223: FS, SNIP-237: FS, SNIP-240: FF, SNIP-238: FF, SNIP-234: FS, SNIP-168: FF, SNIP-178: FF, SNIP-182: FF -4 | 11
NPI Facility Detailed Layout |  | 10 | 05-Aug-26 A | 2026-09-14 |  |  | 16
SNIP-168 | Snip Facility Detailed Roads and Access layout | 10 | 05-Aug-26 A | 2026-09-14 | SNIP-166: FF, SNIP-220: FF | SNIP-240: FF 10 | 16
SNIP-178 | Snip Facility Detailed building layout | 5 | 10-Aug-26 A | 2026-09-14 | SNIP-166: FS, SNIP-220: FF | SNIP-240: FF 15 | 11
Civil |  | 65 | 30-Jun-26 A | 2026-10-02 |  |  | 37
On-Site Waste Dump |  | 18 | 2026-09-08 | 2026-10-02 |  |  | 3
SNIP-146 | Waste Dump & Top-Soil design | 10 | 08-Sep-26* | 2026-09-21 | SNIP-217: SS | SNIP-162: FS | 3
SNIP-162 | Waste Dump MTO | 8 | 2026-09-22 | 2026-10-02 | SNIP-146: FS | SNIP-240: FF 10 | 3
SNIP Water Management |  | 20 | 2026-08-31 | 2026-09-28 |  |  | 6
SNIP-140 | SNIP water management & design (HOLD) | 10 | 2026-08-31 | 2026-09-14 | SNIP-217: SS | SNIP-160: FS | 6
SNIP-160 | SNIP water MTOs. | 10 | 2026-09-15 | 2026-09-28 | SNIP-140: FS | SNIP-240: FF 10 | 6
Design Criteria |  | 1 | 06-Jul-26 A | 07-Jul-26 A
SNIP-116 | Civil Design Criteria-Review & Validate Eskay Creek | 1 | 06-Jul-26 A | 07-Jul-26 A | SNIP-115: FS, SNIP-105: FS | SNIP-125: FS, SNIP-120: SS 3, SNIP-237: FS
3D Model |  | 25 | 19-Aug-26 A | 2026-09-23 |  |  | 4
SNIP-217 | Earthworks 3D Model (On-Site) | 25 | 19-Aug-26 A | 2026-09-23 | SNIP-166: FS | SNIP-237: FS, SNIP-146: SS, SNIP-140: SS, SNIP-222: FF -5 | 4
Bronson Connector Road Design Review Memo |  | 13 | 30-Jun-26 A | 28-Jul-26 A
SNIP-159 | Bronson Connector Road- Acceptance Review Memo-Issue for Internal Review | 3 | 30-Jun-26 A | 03-Jul-26 A | SNIP-136: SS, SNIP-104: FS, SNIP-166: SS | SNIP-164: FS
SNIP-164 | Bronson Connector Road- Acceptance Review Memo-Internal Review, Update and Issue for Client Review | 2 | 06-Jul-26 A | 07-Jul-26 A | SNIP-159: FS | SNIP-169: FS
SNIP-169 | Bronson Connector Road- Acceptance Review Memo-Client Review | 5 | 08-Jul-26 A | 14-Jul-26 A | SNIP-164: FS | SNIP-174: FS
SNIP-174 | Bronson Connector Road- Update and issue Memo-Final Issue | 10 | 15-Jul-26 A | 28-Jul-26 A | SNIP-169: FS | SNIP-198: FS
Foundation(NPI & Portals ) |  | 10 | 10-Aug-26 A | 2026-09-04 |  |  | 55
SNIP-125 | Foundation Recomendations | 10 | 10-Aug-26 A | 2026-09-04 | SNIP-215: SS, SNIP-116: FS |  | 55
MTO |  | 27 | 24-Aug-26 A | 2026-10-01 |  |  | 4
SNIP-198 | Bronson Connector Road -MTO and Model Review | 5 | 24-Aug-26 A | 2026-09-01 | SNIP-174: FS | SNIP-240: FF 15 | 19
SNIP-222 | Preliminary Earthworks MTO (Snip) | 5 | 2026-09-10 | 2026-09-17 | SNIP-217: FF -5 | SNIP-237: FS | 9
SNIP-237 | Earthworks MTO (Snip) | 5 | 2026-09-24 | 2026-10-01 | SNIP-217: FS, SNIP-222: FS, SNIP-116: FS, SNIP-166: FF, SNIP-220: FS, SNIP-105: FS, SNIP-166: FS, SNIP-133: SS, SNIP-115: SS | SNIP-240: FF 10, SNIP-238: FF, SNIP-234: FS -10 | 4
Structural & Concrete |  | 50 | 15-Jul-26 A | 2026-09-24 |  |  | 8
SNIP-215 | Structural & concrete Design/Calc | 25 | 10-Aug-26 A | 2026-09-16 | SNIP-166: FS, SNIP-120: FS | SNIP-125: SS, SNIP-240: FF, SNIP-239: FS, SNIP-234: FS -10, SNIP-239: SS | 9
Structural Design Criteria |  | 1 | 16-Jul-26 A | 16-Jul-26 A
SNIP-120 | Structural Design Criteria-Adopt Eskay Creek | 1 | 16-Jul-26 A | 16-Jul-26 A | SNIP-116: SS 3, SNIP-105: FS | SNIP-215: FS
Snip Building List |  | 50 | 15-Jul-26 A | 2026-09-24 |  |  | 8
SNIP-188 | NPI Major Infrastructure Building List-Issue for Internal Review | 10 | 15-Jul-26 A | 2026-09-02 | SNIP-106: FS | SNIP-197: FS | 8
SNIP-179 | Snip faciliy Building List | 10 | 10-Aug-26 A | 2026-09-02 | SNIP-166: FS | SNIP-240: FF 15 | 18
SNIP-197 | NPI Major Infrastructure Building List-Internal Review, Update and Issue for Client Review | 5 | 2026-09-03 | 2026-09-10 | SNIP-188: FS | SNIP-208: FS | 8
SNIP-208 | NPI Major Infrastructure Building List-Client Review | 5 | 2026-09-11 | 2026-09-17 | SNIP-197: FS | SNIP-212: FS | 8
SNIP-212 | NPI Major Infrastructure Building List-Final Issue | 5 | 2026-09-18 | 2026-09-24 | SNIP-208: FS | SNIP-240: FF 10 | 8
Concrete MTO |  | 5 | 2026-09-17 | 2026-09-23 |  |  | 9
SNIP-239 | Concrete MTO | 5 | 2026-09-17 | 2026-09-23 | SNIP-220: FS, SNIP-215: FS, SNIP-215: SS, SNIP-166: FS | SNIP-238: FF, SNIP-240: FF 10 | 9
Electrical & Instrumentation |  | 61 | 16-Jul-26 A | 2026-10-14 |  |  | 2
Design Criteria |  | 1 | 16-Jul-26 A | 16-Jul-26 A
SNIP-124 | Electrical & Instrumentation Design Criteria -Adopt Eskay Creek | 1 | 16-Jul-26 A | 16-Jul-26 A | SNIP-115: FS, SNIP-105: FS | SNIP-165: FS
Snip Load List |  | 28 | 17-Aug-26 A | 2026-09-24 |  |  | 9
SNIP-165 | Snip Electrical Load List-Issue for Internal Review | 10 | 17-Aug-26 A | 28-Aug-26 A | SNIP-124: FS, SNIP-161: FF 5 | SNIP-126: SS, SNIP-171: FS, SNIP-186: FS, SNIP-170: FF 1
SNIP-171 | Snip Electrical Load List -Internal Review, Update and issue for Client Review | 5 | 31-Aug-26 A | 2026-09-02 | SNIP-165: FS | SNIP-186: FS | 9
SNIP-186 | Snip Electrical Load List - Client Review | 5 | 2026-09-03 | 2026-09-10 | SNIP-161: FS, SNIP-171: FS, SNIP-165: FS | SNIP-228: FS | 9
SNIP-228 | Snip Electrical Load List-Final Issue | 10 | 2026-09-11 | 2026-09-24 | SNIP-231: FF, SNIP-186: FS, SNIP-143: FF 5 | SNIP-227: FF, SNIP-229: FF | 9
Eskay Load List |  | 23 | 17-Aug-26 A | 2026-09-17 |  |  | 14
A1000 | Update Eskay Electrical Load List-Issue for internal Review | 5 | 17-Aug-26 A | 27-Aug-26 A | SNIP-271: FS, SNIP-281: FS | A1010: FS
A1010 | Update Eskay Electrical Load List -Internal Review, Update and Issue for Client Review | 5 | 28-Aug-26 A | 2026-09-02 | A1000: FS | A1020: FS | 14
A1020 | Update Eskay Electrical Load List - Client Review | 5 | 2026-09-03 | 2026-09-10 | A1010: FS | A1030: FS | 14
A1030 | Update Eskay Electrical Load List-Final Issue | 5 | 2026-09-11 | 2026-09-17 | A1020: FS | SNIP-229: FF | 14
Snip HV SLD |  | 27 | 18-Aug-26 A | 2026-09-24 |  |  | 9
SNIP-170 | Snip Single Line Diagrams-Issue for Internal Review | 10 | 18-Aug-26 A | 2026-09-01 | SNIP-165: FF 1, SNIP-190: FS | SNIP-181: FS, SNIP-180: FS -5, SNIP-229: FS | 8
SNIP-181 | Snip Single Line Diagram- Internal Review, Update and Issue for Client Review | 5 | 2026-09-02 | 2026-09-09 | SNIP-170: FS | SNIP-192: FS | 10
SNIP-192 | Snip Single Line Diagrams-Client Review | 5 | 2026-09-10 | 2026-09-16 | SNIP-181: FS | SNIP-229: FS | 10
SNIP-229 | Snip Single Line Diagrams-final Issue-Final Issue | 5 | 2026-09-18 | 2026-09-24 | SNIP-192: FS, SNIP-228: FF, SNIP-170: FS, A1030: FF | SNIP-230: FF, SNIP-238: FF, SNIP-234: FS | 9
Equipment List |  | 51 | 27-Jul-26 A | 2026-10-08 |  |  | 0
SNIP-190 | Snip EEL Inputs (Through Clarifiction) | 5 | 27-Jul-26 A | 17-Aug-26 A | SNIP-201: FS | SNIP-180: FS, SNIP-170: FS
SNIP-200 | Eskay EEL Inputs | 5 | 2026-08-31 | 2026-09-04 | SNIP-271: FS, SNIP-144: FF | SNIP-180: FS | 0
SNIP-180 | Electrical Equipment List-Issue for Internal Review | 10 | 2026-09-08 | 2026-09-21 | SNIP-143: FF 1, SNIP-170: FS -5, SNIP-190: FS, SNIP-200: FS | SNIP-193: FS, SNIP-230: FS, SNIP-194: FS | 0
SNIP-193 | Electrical Equipment List-Internal Review, Update and Issue for Client Review | 5 | 2026-09-22 | 2026-09-28 | SNIP-180: FS | SNIP-205: FS | 0
SNIP-205 | Electrical Equipment List-Client Review | 2 | 2026-09-29 | 2026-10-01 | SNIP-193: FS | SNIP-230: FS | 0
SNIP-194 | Priced Electrical Equipment List | 10 | 2026-09-22 | 2026-10-06 | SNIP-126: FS, SNIP-180: FS | SNIP-206: FS, SNIP-240: FF 10 | 1
SNIP-230 | Electrical Equipment List-Final Issue | 5 | 2026-10-02 | 2026-10-08 | SNIP-205: FS, SNIP-229: FF, SNIP-180: FS | SNIP-234: FS -10, SNIP-240: FF 9, SNIP-238: FF | 0
Generator Sizing Report |  | 15 | 17-Aug-26 A | 2026-09-04 |  |  | 11
SNIP-126 | Generator Sizing Report-snip | 15 | 17-Aug-26 A | 2026-09-04 | SNIP-165: SS, SNIP-106: FS | SNIP-206: FS, SNIP-194: FS | 11
Electrical Update |  | 5 | 2026-10-07 | 2026-10-14 |  |  | 2
SNIP-206 | Factored Electrical Update- Eskay Creeck /Tailing Expansion | 5 | 2026-10-07 | 2026-10-14 | SNIP-126: FS, SNIP-194: FS | SNIP-224: FF | 2
Site Services |  | 15 | 2026-08-31 | 2026-09-21 |  |  | 6
SNIP-202 | Fire Detection and Protection Design (Internal) | 15 | 31-Aug-26* | 2026-09-21 | SNIP-166: FS | SNIP-240: FF 15 | 6
Project Execution Plan / Schedule |  | 20 | 2026-08-31 | 2026-09-28 |  |  | 39
SNIP-214 | Construction Execution Plan | 15 | 2026-08-31 | 2026-09-21 | SNIP-236: SS | SNIP-191: FS | 44
SNIP-218 | Project Execution Plan (PEP) | 15 | 2026-09-08 | 2026-09-28 | SNIP-236: SS 5 | SNIP-219: FF, SNIP-255: FF 10 | 20
SNIP-236 | Project Execution Schedule | 20 | 2026-08-31 | 2026-09-28 | SNIP-161: SS | SNIP-240: FF 10, SNIP-214: SS, SNIP-218: SS 5 | 6
Capital and Operating Cost Estimate |  | 83 | 14-Jul-26 A | 2026-11-12 |  |  | 0
SNIP-152 | Estimate Development Plan and Material Take-off Template | 15 | 20-Jul-26 A | 21-Aug-26 A | SNIP-142: SS 5 | SNIP-240: FS
SNIP-142 | Confirm WBS | 10 | 14-Jul-26 A | 2026-09-04 | SNIP-105: FS 25 | SNIP-152: SS 5, SNIP-270: FS | 11
SNIP-270 | 3rd Party CAPEX Inputs | 0 |  | 2026-09-11 | SNIP-203: FS, SNIP-204: FS, SNIP-320: FS, SNIP-142: FS | SNIP-240: FF 20 | 8
SNIP-310 | 3rd Party OPEX Inputs (SRK) | 0 |  | 2026-09-11 | SNIP-203: FS | SNIP-227: FF 15 | 9
SNIP-211 | Owners Cost Data Entry | 5 | 2026-09-09 | 2026-09-15 | SNIP-240: SS | SNIP-241: FS, SNIP-244: FS, SNIP-224: FF 5 | 16
SNIP-227 | Draft OPEX Development | 20 | 31-Aug-26 A | 2026-10-02 | SNIP-228: FF, SNIP-154: FF, SNIP-310: FF 15 | SNIP-224: FF | 9
SNIP-224 | CAPEX and OPEX Project Review | 5 | 2026-10-07 | 2026-10-14 | SNIP-206: FF, SNIP-227: FF, SNIP-211: FF 5 | SNIP-226: FS, SNIP-235: FS, SNIP-241: FS, SNIP-232: FF | 2
SNIP-232 | Draft Basis of Estimate | 20 | 2026-09-15 | 2026-10-14 | SNIP-224: FF | SNIP-244: FF 10, SNIP-241: FF 5, SNIP-253: FS 5 | 2
SNIP-240 | Draft CAPEX Development | 30 | 2026-09-09 | 2026-10-22 | SNIP-270: FF 20, SNIP-204: FF 20, SNIP-203: FF 20, SNIP-178: FF 15, SNIP-168: FF 10, SNIP-179: FF 15, SNIP-202: FF 15, SNIP-198: FF 15, SNIP-156: FF, SNIP-195: FF 15, SNIP-162: FF 10, SNIP-236: FF 10, SNIP-194: FF 10, SNIP-231: FF 10, SNIP-215: FF, SNIP-237: FF 10, SNIP-239: FF 10, SNIP-143: FF 10, SNIP-152: FS, SNIP-160: FF 10, SNIP-220: FF, SNIP-105: FF, SNIP-166: FF, SNIP-133: SF, SNIP-115: SF, SNIP-230: FF 9, SNIP-320: FF 20, SNIP-212: FF 10 | SNIP-242: FF 2, SNIP-241: FF 1, SNIP-244: FS, SNIP-211: SS | 0
SNIP-241 | Ausenco Corporate Estimate Review and Updates | 5 | 2026-10-19 | 2026-10-23 | SNIP-211: FS, SNIP-240: FF 1, SNIP-224: FS, SNIP-235: FS, SNIP-226: FS, SNIP-232: FF 5 | SNIP-249: FF, SNIP-258: FF, SNIP-248: FF, SNIP-255: FF 2, SNIP-244: FS | 0
SNIP-244 | Client CAPEX and OPEX Final Review | 5 | 2026-10-26 | 2026-10-30 | SNIP-211: FS, SNIP-240: FS, SNIP-241: FS, SNIP-232: FF 10 | SNIP-280: FF 2, SNIP-252: FS, SNIP-249: FF, SNIP-255: FF, SNIP-251: FS, SNIP-250: FS, SNIP-247: FF, SNIP-246: FF, SNIP-258: FF 5 | 0
SNIP-250 | CAPEX - Issued Final | 5 | 2026-11-02 | 2026-11-06 | SNIP-244: FS | SNIP-249: FF, SNIP-258: FF, SNIP-248: FF, SNIP-255: FF, SNIP-253: FF 3, SNIP-246: FF | 0
SNIP-251 | OPEX - Issued Final | 5 | 2026-11-02 | 2026-11-06 | SNIP-244: FS | SNIP-253: FF 3, SNIP-247: FF | 0
SNIP-253 | Final Basis of Estimate | 5 | 2026-11-05 | 2026-11-12 | SNIP-251: FF 3, SNIP-250: FF 3, SNIP-232: FS 5 | SNIP-255: FF | 0
Financial Model |  | 31 | 2026-09-25 | 2026-11-10 |  |  | 11
SNIP-290 | Client Input to Model (Offsite Charges & Tax) | 0 |  | 2026-09-25 | SNIP-242: SF |  | 42
SNIP-242 | Financial Model - Issue for Client Review | 20 | 2026-09-25 | 2026-10-26 | SNIP-117: FS, SNIP-157: FS, SNIP-240: FF 2 | SNIP-290: SF, SNIP-254: FF, SNIP-252: FS | 5
SNIP-254 | Sensitivity Analysis | 3 | 2026-10-22 | 2026-10-26 | SNIP-242: FF | SNIP-257: FS | 10
SNIP-252 | Financial Model - Client Review | 5 | 2026-11-02 | 2026-11-06 | SNIP-244: FS, SNIP-242: FS | SNIP-257: FS, SNIP-255: FF | 1
SNIP-257 | Financial Model & DCF Economic Metrics Report - Final Issue | 2 | 2026-11-09 | 2026-11-10 | SNIP-252: FS, SNIP-254: FS | SNIP-280: FF, SNIP-255: FF | 1
Technical Report |  | 70 | 17-Aug-26 A | 2026-11-26 |  |  | 0
SNIP-183 | Draft TOC for Client Review | 10 | 17-Aug-26 A | 2026-09-11 | SNIP-105: FS 70 | SNIP-255: FS | 1
SNIP-280 | News Release | 0 |  | 2026-11-10 | SNIP-257: FF, SNIP-244: FF 2 | SNIP-259: FS | 6
SNIP-255 | Draft Report | 40 | 2026-09-15 | 2026-11-12 | SNIP-257: FF, SNIP-252: FF, SNIP-244: FF, SNIP-101: SF, SNIP-111: SF, SNIP-250: FF, SNIP-183: FS, SNIP-155: FF, SNIP-134: FF, SNIP-154: FF, SNIP-241: FF 2, SNIP-234: FF 10, SNIP-218: FF 10, SNIP-253: FF | SNIP-245: FF -10, SNIP-256: FS, SNIP-258: FS | 0
SNIP-258 | Draft Report Client Review | 5 | 2026-11-13 | 2026-11-19 | SNIP-101: SF, SNIP-111: SF, SNIP-241: FF, SNIP-250: FF, SNIP-244: FF 5, SNIP-255: FS, SNIP-256: FS | SNIP-259: FS | 0
SNIP-259 | Report Update and Finalization | 5 | 2026-11-20 | 2026-11-26 | SNIP-258: FS, SNIP-133: SS, SNIP-115: SS, SNIP-161: FS, SNIP-280: FS | SNIP-260: FS | 0